Njaz.org

Project Plan

Arabic Psychometrics and Surveys Application

Khaled Rashwan 6-2-2024

Contents

Phase 1: Planning (5 weeks)	1

Phase 2: Development (9 weeks)	2

Phase 3: Testing (5 weeks)	2

Phase 4: Deployment (3 weeks)	3

Phase 5: Maintenance (Ongoing)	4

# Project Plan with Dates

# Phase 1: Planning (5 weeks)

Week 1-2: Requirement Analysis

- Dates: September 11, 2024 – September 24, 2024

- Tasks:

  - Define the features and functionalities of the application through stakeholder interviews, surveys, and market analysis.

  - Identify user roles (researcher, admin).

- Deliverable: Requirement Analysis Document

Week 3: Buffer for Requirement Analysis

- Dates: September 25, 2024 – October 1, 2024

Week 4: Project Setup

- Dates: October 2, 2024 – October 8, 2024

- Tasks:

  - Set up a project repository (e.g., GitHub, GitLab).

  - Configure Expo for React Native.

Week 5: Design

- Dates: October 9, 2024 – October 15, 2024

- Tasks:

  - Create wireframes and UI/UX designs for the application.

  - Define the data model for psychometrics and surveys.

- Deliverable: Design Documentation

Milestones:

- End of Week 3 (October 1, 2024): Complete Requirement Analysis Document.

- End of Week 5 (October 15, 2024): Complete Design Documentation.

# Phase 2: Development (9 weeks)

Week 6-7: Frontend Development

- Dates: October 16, 2024 – October 29, 2024

- Tasks:

  - Build user interfaces using React Native and Expo.

  - Create Development Documentation.

Week 8-9: Backend Development

- Dates: October 30, 2024 – November 12, 2024

- Tasks:

  - Develop APIs and services using AWS.

Week 10-11: Database Setup

- Dates: November 13, 2024 – November 26, 2024

- Tasks:

  - Configure the database.

  - Define Database Schema.

Week 12-13: Integration

- Dates: November 27, 2024 – December 10, 2024

- Tasks:

  - Integrate frontend, backend, and database.

Week 14: Buffer for Development

- Dates: December 11, 2024 – December 17, 2024

Milestones:

- End of Week 14 (December 17, 2024): Complete Development Documentation.

# Phase 3: Testing (5 weeks)

Week 15-16: Unit Testing

- Dates: December 18, 2024 – December 31, 2024

- Tasks:

  - Write unit tests for frontend and backend components.

  - Document Testing Procedures.

Week 17: Integration Testing

- Dates: January 1, 2025 – January 7, 2025

- Tasks:

  - Test interactions between frontend and backend.

Week 18: User Acceptance Testing

- Dates: January 8, 2025 – January 14, 2025

- Tasks:

  - Conduct UAT with a group of researchers to gather feedback.

  - Document Test Results.

Week 19: Buffer for Testing

- Dates: January 15, 2025 – January 21, 2025

Milestones:

- End of Week 19 (January 21, 2025): Complete Testing Documentation.

# Phase 4: Deployment (3 weeks)

Week 20: Deployment to AWS

- Dates: January 22, 2025 – January 28, 2025

- Tasks:

  - Set up CI/CD pipelines using AWS services (CodePipeline, CodeBuild).

  - Create Deployment Plan.

Week 21: Launch

- Dates: January 29, 2025 – February 4, 2025

- Tasks:

  - Submit apps to Google Play and Apple App Store.

  - Launch web version.

Week 22: Buffer for Deployment

- Dates: February 5, 2025 – February 11, 2025

Milestones:

- End of Week 22 (February 11, 2025): Deployment and Launch.

# Phase 5: Maintenance (Ongoing)

Week 23+: Maintenance and Updates

- Start Date: February 12, 2025

- Tasks:

  - Track issues and bugs.

  - Release updates and enhancements.

  - Maintain Change Logs and Issue Tracking.

Key Milestones:

- Ongoing: Maintenance Documentation and Updates.